## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Notes | Date started (actual date) | Date finished (actual date)
G32-US1 | Create Virtual Bank Accounts | 1. Users can create both current and savings accounts through the application. 2. Account information includes username, password, and account type. 3. Input information must pass validation checks. | High | First Iteration | 1. Users input username and password. 2. Users select the account type (current account or savings account). 3. Upon submission, system validates username and password format. | Ensure password complexity requirements. | 2024-04-01 | 2024-04-02
G32-US2 | Balance Tracking | 1. Upon user login, the application displays their current account balance. 2. Balance should be displayed in currency format and updated in real-time. | High | First Iteration | 1. Users log in to the application. 2. Application displays account balance. | Ensure real-time update of balance. | 2024-04-03 | 2024-04-03
G32-US3 | Deposit | 1. Users can deposit virtual currency earned by completing tasks into their accounts. 2. Deposited amount should be added to the account balance and display the updated balance. 3. After a successful deposit, the application displays the updated account balance. | Medium | First Iteration | 1. Users select deposit action. 2. Users input deposit amount. 3. Application displays the latest account balance. |  | 2024-04-04 | 2024-04-05
G32-US4 | Withdrawal | 1. Users can withdraw virtual currency from their accounts. 2. Withdrawn amount should be deducted from the account balance and display the updated balance. | Medium | Second Iteration | 1. Users select withdrawal action. 2. Application displays the updated account balance. |  | 2024-04-16 | 2024-04-17
G32-US5 | Task Setting | 1. Parents can set tasks or activities and assign corresponding rewards. 2. Children can view the task list and choose to complete tasks to earn rewards. 3. After rewards are assigned, the application adds rewards to children's accounts. | High | Second Iteration | 1. Parents log in and select task setting. 2. Children log in and view task list. 3. Application updates account balance. | Ensure task setting interface is intuitive. | 2024-04-18 | 2024-04-19
G32-US6 | Transaction History | 1. Users can view the transaction history of their accounts. 2. Transaction history should include date, transaction type, and amount. | Medium | Third Iteration | 1. Users log in and select view transaction history. 2. Application displays transaction history. |  | 2024-04-29 | 2024-05-01
G32-US7 | Savings Goals | 1. Children can set savings goals and track their progress. 2. The application should display the goal amount, current progress, and remaining amount. | High | Third Iteration | 1. Children log in and select set savings goals. 2. Application displays goal progress and remaining amount. | Ensure progress tracking is visually clear. | 2024-05-07 | 2024-05-08
G32-AF1 | Additional Features | To be determined based on specific requirements. | Low | Fourth Iteration | To be determined based on specific feature requirements. |  | 2024-05-13 | 2024-05-24